## Tasks
WardThread — HACK_002 Task Tracker
Edit only the yellow columns (Owner, Status, Notes). Status & Owner are dropdowns. Row turns green when Completed, red when Blocked.
ID | Milestone | Area | Task | Owner | Status | Target (CEST) | Brief ref | Notes / blocker
T01 | M0 | Setup | Create npm workspaces root (server, web), scripts dev/test/eval, .gitignore, .env.example | Omar | Not started | 14:30 | §4 §6 §7
T02 | M0 | Setup | Corti Console: create API client, put creds in server/.env only, pin @corti/sdk version | Hassan | Not started | 14:30 | §5
T03 | M0 | Frontend | Create Lovable project (Vite+React+TS+Tailwind), 4 tabs shell, connect to GitHub | Saad | Not started | 14:30 | §4 §19
T04 | M0 | Integration | Agree API response shapes (share types.ts + sample JSON for every /api route with Saad) | Omar | Not started | 15:00 | §17
T05 | M1 | Backend | db.ts: SQLite schema on boot (all 9 tables) | Hassan | Not started | 15:30 | §8
T06 | M1 | Backend | clock.ts: simulated clock, seed Sat 09:00, GET /clock, POST /clock/advance | Hassan | Not started | 16:00 | §16
T07 | M1 | Backend | fixtures: beds.json (6 beds, bed 4 with approved task due soon) + seed.ts + POST /reset | Hassan | Not started | 16:30 | §3 §6
T08 | M1 | Backend | domain/types.ts + state-machine.ts (InvalidTransition → 409, activity row per transition) | Omar | Not started | 16:30 | §10
T09 | M1 | Backend | deadlines.ts: resolve today/tomorrow/before_discharge/none against sim clock | Omar | Not started | 17:00 | §9
T10 | M1 | Backend | downstream/task-system.ts SIMULATED: createTask (idempotent), getTask, markDone | Hassan | Not started | 17:00 | §15
T11 | M1 | Backend | Routes: threads approve / edit-approve / dismiss + readback → verified ¦ failed_verification | Omar | Not started | 17:30 | §10 §15 §17
T12 | M1 | Backend | rollup.ts + GET /beds (priority order, per-state counts) | Hassan | Not started | 17:30 | §18
T13 | M1 | Backend | Routes: GET /tasks?team=, POST /tasks/:id/done, GET /threads/:id/activity | Hassan | Not started | 18:00 | §17
T14 | M1 | Backend | Tests: state machine + DEDICATED test 'task only created from approved' | Omar | Not started | 18:00 | §10
T15 | M2 | Backend | corti/gateway.ts interface + LiveCortiGateway (auth, mintToken, 60s timeout, 1 retry, usage log) | Hassan | Not started | 19:00 | §11
T16 | M2 | Backend | corti/cache.ts sha256 JSON cache + fake.ts FakeCortiGateway; CACHE_MODE readonly works offline | Hassan | Not started | 19:30 | §11 §14
T17 | M2 | Backend | pipeline/extract.ts: documents.generate dynamic template + outputSchema, zod validate, retry once | Omar | Not started | 19:30 | §14
T18 | M2 | Backend | pipeline/ground.ts (verbatim quote in ONE final segment) + dedup.ts (token overlap ≥0.6) | Omar | Not started | 20:00 | §13
T19 | M2 | Backend | pipeline/run.ts: persist proposed threads + activity trail + rejected_candidates | Omar | Not started | 20:30 | §13
T20 | M2 | Backend | Input C: POST /sessions/:id/text; Input B: POST /sessions {bedId, caseId} pre-recorded STT | Hassan | Not started | 20:30 | §12
T21 | M2 | Backend | GET /sessions/:id, GET /threads?bedId=, GET /health (corti ok¦error) | Hassan | Not started | 21:00 | §11 §17
T22 | M2 | Content | Write case-01..06 script.txt + gold.json (incl. 2 honest failures); record/generate audio | Omar + Hassan | Not started | 21:00 | §6 §3.7
T23 | M3 | Frontend | Session page: bed picker, record/play clip buttons, live transcript, RecordingIndicator | Saad | Not started | 18:00 | §3 §12
T24 | M3 | Frontend | ThreadCard: approve / edit (team, deadline, urgency) / dismiss with reason; quote highlight in transcript | Saad | Not started | 19:00 | §3
T25 | M3 | Frontend | StatusRing + ActivityTrail components (Proposed/Tracked/Verified/Escalated states) | Saad | Not started | 19:30 | §10 §18
T26 | M3 | Frontend | Ward Board page: BedRow per bed, rollup, red 'Escalated', 'No tracked follow-through blockers' wording | Saad | Not started | 20:00 | §18
T27 | M3 | Frontend | Tasks page: SIMULATED team queues, Mark done button; 'Advance clock 24h' + 'Reset demo' buttons | Saad | Not started | 20:30 | §15 §16
T28 | M3 | Frontend | Eval page: EvalTable, metrics, before/after workflow map | Saad | Not started | 21:00 | §2 §3.7
T29 | M3 | Frontend | 'SIMULATED' labels everywhere; never show 'clear for discharge' | Saad | Not started | 21:00 | §0 §1
T30 | M4 | Integration | Export Lovable code into web/, strip Supabase/any Lovable backend, api.ts with plain fetch + 2s polling | Omar | Not started | 22:00 | §4 §6
T31 | M4 | Integration | Wire Session → pipeline → ThreadCards; Approve → PHA-#### in queue → ring green 'Verified' | Omar | Not started | 23:00 | §3.3
T32 | M4 | Integration | Record cached run of demo case so step 3 works with CORTI_MODE=fake / no network | Hassan | Not started | 23:30 | §3 §14
T33 | M5 | Backend | POST /sessions/ambient (interactions.create + streams token) + /segments + /finish | Hassan | Not started | 23:30 | §12A
T34 | M5 | Integration | web/corti-stream.ts: stream.connect facts mode, live transcript, end/ENDED, mic release; fallback 'Use recorded clip' | Omar | Not started | 00:30 | §12A
T35 | M5 | Backend | Escalation sweep on clock advance; escalated → verified when task done | Hassan | Not started | 00:00 | §10 §16
T36 | M5 | Backend | eval/run.ts: 6 cases → accuracy, human corrections, time saved vs manual-baseline.json → metrics.json + GET /eval | Hassan | Not started | 00:45 | §1.7 §2
T37 | M5 | Integration | Full demo path steps 1–7 passes in browser (run 3× clean) | Omar | Not started | 01:00 | §3
T38 | M6 | QA | Bug-fix pass only; offline rehearsal with CACHE_MODE=readonly | All | Not started | 04:00 | §0.8
T39 | M6 | Docs | README (before/after workflow map, decision owners, metrics) + DISCLOSURE.md | Omar | Not started | 05:00 | §2
T40 | M6 | Demo | Record 2-min demo video (no creds on screen) | All | Not started | 07:00 | §0 §5
T41 | M6 | Submission | ZIP git repo (exclude .env, data/, .cache/, node_modules) + submit Google Form | Omar | Not started | 08:00 | §0
Note on G4: Build window Sat 26 Sep 13:00 → Sun 27 Sep 08:30 CEST; submit by 08:00. Times after midnight are Sunday. Targets are my proposal — adjust.

## Milestones
Milestones
Progress columns are formulas driven by the Tasks sheet — do not edit them.
ID | Milestone | Deadline (CEST) | Done when… | Tasks | Completed | In progress | Blocked | % done | Status
M0 | Repo + skeleton running | Sat 26 Sep 14:30 | npm run dev boots server :8787 + web; .env.example; .gitignore
M1 | Backend core (no AI) | Sat 26 Sep 18:00 | DB, clock, state machine, SIMULATED task system, approve→task→readback via API, tests green
M2 | Corti + pipeline (text path) | Sat 26 Sep 21:00 | Text/pre-recorded input → extract → ground → dedup → proposed threads; cache + fake mode
M3 | Frontend screens (Lovable) | Sat 26 Sep 21:00 | Session, Ward Board, Tasks, Eval pages built on mock data matching API shapes
M4 | MAGIC MOMENT end-to-end | Sat 26 Sep 23:30 | Demo step 3 works in browser, live AND cached/offline
M5 | Full demo path + eval — FEATURE FREEZE | Sun 27 Sep 01:00 | Ambient live, edit/dismiss, clock+escalation, Eval page with 6 cases
M6 | Hardening + submission | Sun 27 Sep 08:00 | Bug fixes only, README/DISCLOSURE, 2-min video, ZIP, Google Form submitted
Hard rule: after 01:00 Sunday (M5) → bug fixes only, no new features, no refactors (Brief §0.8).

## Team
Who is doing what
Owner | Role | Tasks | Completed | In progress | Blocked | Not started | % done
Omar | Backend (state machine, pipeline) → then owns front↔back integration & demo path
Hassan | Backend (DB, clock, task system, Corti gateway, eval)
Saad | Frontend in Lovable (all 4 pages, components)
Omar + Hassan | Shared backend content (case scripts, gold labels)
All | Final QA, video
TOTAL
Assumptions (correct if wrong):
• 'Me' in the brief = Omar (the one who later connects back and front).
• Lovable exports React+Vite+TS+Tailwind; its Supabase backend must NOT be used — web/ talks only to our Express server via fetch (Brief §4).
• Saad builds on mock JSON matching the agreed API shapes (task T04) so integration at M4 is a swap, not a rewrite.
• Target times are proposals; brief §19 (UI) was cut off in what I received, so UI tasks follow §3 demo + §6 components.