## Tasks
Orchestra — HACK_002 Task Tracker
Edit only the yellow columns (Owner, Status, Notes). Status & Owner are dropdowns. Row turns green when Completed, red when Blocked.
ID | Milestone | Area | Task | Owner | Status | Target (CEST) | Plan ref | Notes / blocker
T01 | M0 | Docs | MVP plan + Lovable plan written, reviewed, merged | Omar | Completed | 20:30 | MVP_PLAN
T02 | M1 | Backend | New schema, 3-layer visibility rule, login + agent keys | Omar | Not started | 21:00 | MVP_PLAN
T03 | M1 | Backend | REST endpoints exactly matching LOVABLE_PLAN §4 (filters, review_queue, graph) | Omar | Not started | 21:30 | LOVABLE §4
T04 | M1 | Backend | MCP tools: start/report/attach/submit, live agent presence, mention extraction | Omar | Not started | 22:00 | MVP_PLAN
T05 | M1 | Backend | Seed: Northwind project matching LOVABLE §7 (deps, mentions, live tasks) | Hassan | Completed | 21:30 | LOVABLE §7 | northwind.json polished: every task has a description + scope, fuller KB docs, 12 mention links in the graph, one believable overdue task (T-2).
T06 | M1 | Backend | Webhooks on task events (open-source integration story) | Hassan | Completed | 22:00 | MVP_PLAN | Built in the backend rewrite: server/src/webhooks.ts, POST /api/webhooks (PM). Covered by api.test.ts.
T07 | M1 | Backend | npm run sim: simulated agents John/Priya/Mia via real MCP | Hassan | Completed | 22:30 | MVP_PLAN | PR #6 merged. npm run sim (-- --reset). Agent scripts: server/sim/stories/northwind.json. Works hosted (--url) and with random keys.
T08 | M2 | Frontend | Paste LOVABLE_PLAN into Lovable; shell, routes, login, mock mode | Saad | Not started | 20:45 | LOVABLE §10
T09 | M2 | Frontend | Board + task drawer (timeline, markdown, artifacts) | Saad | Not started | 21:30 | LOVABLE §5
T10 | M2 | Frontend | PM graph (react-force-graph-2d) with buildGraph() mock | Saad | Not started | 22:00 | LOVABLE §6
T11 | M2 | Frontend | Activity, Knowledge, Review, Live agents rail | Saad | Not started | 22:00 | LOVABLE §5
T12 | M3 | Integration | Switch UI to LIVE; fix contract mismatches | Omar | Not started | 23:30 | LOVABLE §4
T13 | M3 | Integration | Connect Claude Code as a junior agent; run a task end-to-end | Omar | Not started | 00:00
T14 | M3 | Integration | Sim agents + real Claude Code agent together on the shared server (no staged refusal: team decision) | Hassan | Not started | 00:30
T15 | M4 | QA | Acceptance checklist (LOVABLE §9) 3x after reset | All | Not started | 02:00 | LOVABLE §9
T16 | M4 | Docs | README: pitch, run steps, open source + integrations | Hassan | Not started | 02:00 |  | Simulated agents section added (PR #6). Pitch + integrations still to do.
T17 | M5 | Demo | Record 2-min video | All | Not started | 07:00
T18 | M5 | Submission | ZIP repo + submit form | Omar | Not started | 07:30
Note on G4: Build window Sat 26 Sep 13:00 → Sun 27 Sep 08:30 CEST; submit by 08:00. Times after midnight are Sunday. Targets are my proposal — adjust.

## Milestones
Milestones
Progress columns are formulas driven by the Tasks sheet — do not edit them.
ID | Milestone | Deadline (CEST) | Done when… | Tasks | Completed | In progress | Blocked | % done | Status
M0 | Plans agreed + merged | Sat 26 Sep 20:30 | MVP_PLAN + LOVABLE_PLAN on main
M1 | Backend v1 matches LOVABLE_PLAN | Sat 26 Sep 22:00 | All endpoints + MCP tools + tests green
M2 | UI on mock data | Sat 26 Sep 22:00 | All Lovable screens work in MOCK mode
M3 | LIVE end-to-end | Sun 27 Sep 00:30 | UI on real API; sim agents + Claude Code agent visible live
M4 | Demo polish — FEATURE FREEZE | Sun 27 Sep 02:00 | Acceptance checklist passes 3x after reset
M5 | Submission | Sun 27 Sep 07:30 | Video, ZIP, form submitted
Hard rule: after 02:00 Sunday (M3 freeze) → bug fixes only, no new features, no refactors .

## Team
Who is doing what
Owner | Role | Tasks | Completed | In progress | Blocked | Not started | % done
Omar | Backend core (schema, REST, MCP) → integration, agent demo, submission
Hassan | Seed data, webhooks, simulated agents, README
Saad | Lovable frontend per LOVABLE_PLAN.md
All | QA, video
TOTAL
Assumptions (correct if wrong):
• Source of truth: docs/MVP_PLAN.md (everyone) and docs/LOVABLE_PLAN.md (frontend + API contract).
• Feature freeze 02:00; after that bug fixes only.